## SS summary planned vs ach
Mandatory Disclosure : Supportive Supervision Summary (Planned Vs achieved)
Level | Quarter-1 |  | Quarter-2 |  | Quarter-3 |  | Quarter-4
| Planned visits (numbers) | Achieved (numbers and %) | Planned visits (numbers) | Achieved (numbers and %) | Planned visits (numbers) | Achieved (numbers and %) | Planned visits (numbers) | Achieved (numbers and %)
State | 12 | 9 & 75% | 12 | 8 &66.6% | 12 | 9 & 75% | 12 | NA
Division/ Regional | NA | NA | NA | NA | NA | NA | NA | NA
District | 37 (Total for 11 Districts) | 27 & 77% | 39 (Total for 11 Districts) | 24 & 63.15% | 38 (Total for 11 Districts) | 26 &68.42% | 37 (Total for 11 Districts) | NA
Block | 234 (Total for 39 Blocks) | 116 & 49 % | 234 (Total for 39 Blocks) | 107 & 45% | 234 (Total for 39 Blocks) | 104 & 44% | 234 (Total for 39 Blocks) | NA
Note: Each facility in the State should be visited at least twice a year
As given in the mandatory disclosures, all the SS checklists/reports are to be uploaded on the website.

## Summary action-taken
Month-wise Summary Sheet of action taken
Sl. No. Name of facility Visited | 3 key Issues Identified | Reference (Report: name of supervisor and date) | Action/s recommended and agreed | Action to be taken at what level (State, Division, District, Block, Facility) and by whom | Action taken (Yes/No) | Pending at what level
1 2 3
*** Reports to be uploaded on State NHM Website
*** Most of the reports till 2nd Quarter has been uploaded on the website

## Facilities covered
Facilities covered in Supportive Supervision (All the facilities to be covered atleast twice a year)
Type of facilities | Total existing (numbers) | Quarter -1 |  |  | Quarter-2 |  |  | Quarter-3
|  | Number of facilities covered in Q1 | % facilities covered in Q1 | % visits for which report/action plan available/uploaded | Remaining facilities (numbers) | % remaining facilities covered in Q2 | % visits for which report/action plan available/uploaded | Remaining facilities (numbers) | % remaining facilities covered in Q2 | % visits for which report/action plan available/uploaded
DH | 11 | 4 | 36% | Reports available | 7 | 28.57% | Reports available | 5 | 40% | Reports available
SDH | 1 | 1 | 100% | Reports available | 0 | NA | NA | 0 | NA | NA
FRU | 8 | 3 | 37.5% | Reports available | 5 | 40% | Reports available | 3 | 66% | Reports available
Non FRU CHC | 26 | 5 | 19.2% | Reports available | 21 | 33.3% | Reports available | 14 | 42.8% | Reports available
Block PHC | NA
PHC | 110 | 22 | 20% | Reports available | 88 | 30.6% | Reports available | 61 | 47.5% | Reports available
SC | 433 | 51 | 11.7% | Reports available | 382 | 14.92% | Reports available | 325 | 14.7% | Reports available
VHND sites | 5126 | NA | NA | NA | NA | NA | NA | NA | NA | NA
Others
Facilities under PPP | 22 | 5 | 22.7% | Reports available | 17 | 35.2 | Reports available | 11 | 36.3% | Reports available
The above format needs to be duplicated for Q3 and Q4